## Sprint Plan Currently Project (
Name | Date Created | Sprint | Status
Initialise Git Repo, set up folder structure(frontend, backend & docs) | November 10, 2025 5:00 PM | Sprint One: Project Setup & Architecture | Completed
Configure SpringBoot backend with PostgreSQL DB | November 10, 2025 5:01 PM | Sprint One: Project Setup & Architecture | Completed
Set up react frontend | November 10, 2025 5:01 PM | Sprint One: Project Setup & Architecture | Completed
Taskcreate base react compponents & routing | November 10, 2025 5:01 PM | Sprint One: Project Setup & Architecture | Completed
Create Notion workspace For sprints and documentation | November 10, 2025 5:02 PM | Sprint One: Project Setup & Architecture | Completed
TaskAdd basic README & Project Guidelines | November 10, 2025 5:02 PM | Sprint One: Project Setup & Architecture | In Progress
Backend:Spring Security, JWT and password hadhing in place | November 10, 2025 5:03 PM | Sprint Two: Sprint 2: Authentication & User Management | Completed
Frontend: Initial lasnding page, Sign Up/ Log In pages, forms and validation | November 10, 2025 5:03 PM | Sprint Two: Sprint 2: Authentication & User Management | Completed
Connect Frontend to Backend API points | November 10, 2025 5:04 PM | Sprint Two: Sprint 2: Authentication & User Management | Completed
Test user auth and session management | November 10, 2025 5:04 PM | Sprint Two: Sprint 2: Authentication & User Management | Completed
Document authenticication flow | November 10, 2025 5:04 PM | Sprint Two: Sprint 2: Authentication & User Management | In Progress
Ensure login, dashboard skeleton, and backend endpoints work | November 10, 2025 5:14 PM | Mid Point Presentation | Not Started
Show folder structure, documentation, and initial designs | November 10, 2025 5:15 PM | Mid Point Presentation | Not Started
Compile Notion documentation & sprint progress | November 10, 2025 5:15 PM | Mid Point Presentation | Not Started
Prepare a short demo of initial functionality for presentation | November 10, 2025 5:15 PM | Mid Point Presentation | Not Started
Create Backend with api endpouints getting appliance + room data | November 10, 2025 5:15 PM | Sprint 5: Dashboard Development | Not Started
Frontend: build dashboard page in line with Wireframes | November 10, 2025 5:16 PM | Sprint 5: Dashboard Development | In Progress
Fetch and display live user data, make sure “no data scenario” is handled for new users | November 10, 2025 5:16 PM | Sprint 5: Dashboard Development | Not Started
QA: validate accuracy of fetched data and verify authenticication and data privacy | November 10, 2025 5:17 PM | Sprint 5: Dashboard Development | Not Started
Backend: CRUD API for rooms (user → rooms) | November 10, 2025 5:22 PM | Sprint 4: Map My House Feature | Completed
Frontend: Map My House page, room creation UI, multiple floors | November 10, 2025 5:23 PM | Sprint 4: Map My House Feature | Completed
Link rooms to user accounts | November 10, 2025 5:23 PM | Sprint 4: Map My House Feature | Completed
Unit test room creation & retrieval | November 10, 2025 5:23 PM | Sprint 4: Map My House Feature | In Progress
Backend: CRUD API for appliances (room → appliances) | November 10, 2025 5:23 PM | Sprint 3: My Appliances Feature | Completed
Frontend: Appliance assignment, selection from DB | November 10, 2025 5:24 PM | Sprint 3: My Appliances Feature | Completed
Store appliance usage hours and wattage | November 10, 2025 5:24 PM | Sprint 3: My Appliances Feature | Completed
Test user flows from room creation → appliance assignment | November 10, 2025 5:24 PM | Sprint 3: My Appliances Feature | In Progress
Backend: API endpoints to calculate room consumption and top 5 appliances | November 10, 2025 5:30 PM | Sprint 6: Watch Your Watts page | Not Started
Frontend: Pie charts (Recharts/Chart.js) for rooms | November 10, 2025 5:31 PM | Sprint 6: Watch Your Watts page | Not Started
Cost forecasting based on appliance usage | November 10, 2025 5:31 PM | Sprint 6: Watch Your Watts page | Not Started
Connect predictive model for reduced consumption scenarios | November 10, 2025 5:31 PM | Sprint 6: Watch Your Watts page | Not Started
Test correctness of calculations and visuals | November 10, 2025 5:31 PM | Sprint 6: Watch Your Watts page | Not Started
Test all API connections & user flows | November 10, 2025 5:31 PM | Sprint 7: Integration & Security Hardening | Not Started
Add input validation & error handling | November 10, 2025 5:31 PM | Sprint 7: Integration & Security Hardening | Not Started
Review password storage, JWT expiry, and secure endpoints | November 10, 2025 5:31 PM | Sprint 7: Integration & Security Hardening | Not Started
Document security measures in SECURITY_NOTES.md | November 10, 2025 5:31 PM | Sprint 7: Integration & Security Hardening | Not Started
Begin writing integration tests | November 10, 2025 5:31 PM | Sprint 7: Integration & Security Hardening | Not Started
Unit tests for backend services (JUnit/Mockito) | November 10, 2025 5:32 PM | Sprint 8: Testing & Debugging | Not Started
Integration tests for API & frontend | November 10, 2025 5:32 PM | Sprint 8: Testing & Debugging | Not Started
Test predictive module accuracy | November 10, 2025 5:32 PM | Sprint 8: Testing & Debugging | Not Started
Ensure database consistency and error handling | November 10, 2025 5:32 PM | Sprint 8: Testing & Debugging | Not Started
Prepare test report | November 10, 2025 5:32 PM | Sprint 8: Testing & Debugging | Not Started
Regression tests of all modules | November 10, 2025 5:32 PM | Sprint 11: Final Testing & Submission Polish | Not Started
Add optional features (e.g., custom appliance types, export data)Optimise performance (frontend rendering, backend queries)Update diagrams and architecture documents | November 10, 2025 5:32 PM | Sprint 9: Final Feature Enhancements | Not Started
Proofread documentation, check academic compliance | November 10, 2025 5:33 PM | Sprint 11: Final Testing & Submission Polish | Not Started
Final code review and GitHub commit history clean-up | November 10, 2025 5:33 PM | Sprint 11: Final Testing & Submission Polish | Not Started
Prepare submission zip and presentation slides | November 10, 2025 5:33 PM | Sprint 11: Final Testing & Submission Polish | Not Started
Appliance DB: Create JSON file with list of household appliances which users can assign in “my Appliances” | November 14, 2025 12:07 PM | Sprint 5: Dashboard Development | Completed
Presentation Slides | December 10, 2025 10:00 PM | Mid Point Requirements | Not Started
Technical Report | December 10, 2025 10:00 PM | Mid Point Requirements | Not Started
Update Project Proposal | December 10, 2025 10:01 PM | Mid Point Requirements | Not Started