## Sprint Plan Currently Project (
Name | Sprint | Status
TaskAdd basic README & Project Guidelines | Sprint 1: Project Setup & Architecture | Completed
Initialise Git Repo, set up folder structure(frontend, backend & docs) | Sprint 1: Project Setup & Architecture | Completed
Configure SpringBoot backend with SQLite DB | Sprint 1: Project Setup & Architecture | Completed
Set up react frontend | Sprint 1: Project Setup & Architecture | Completed
create base react components & routing | Sprint 1: Project Setup & Architecture | Completed
Create Notion workspace For sprints and documentation | Sprint 1: Project Setup & Architecture | Completed
Backend:Spring Security, JWT and password hadhing in place | Sprint 2: Authentication & User Management | Completed
Frontend: Initial lasnding page, Sign Up/ Log In pages, forms and validation | Sprint 2: Authentication & User Management | Completed
Connect Frontend to Backend API points | Sprint 2: Authentication & User Management | Completed
Test user auth and session management | Sprint 2: Authentication & User Management | Completed
Document authenticication flow | Sprint 2: Authentication & User Management | In Progress
Create Backend with api endpouints getting appliance + room data | Sprint 5: Dashboard Development | Completed
Frontend: build dashboard page in line with Wireframes | Sprint 5: Dashboard Development | Completed
User can change their cost per KwH | Sprint 5: Dashboard Development | Completed
QA: validate accuracy of fetched data and verify authenticication and data privacy | Sprint 5: Dashboard Development | Completed
Fetch and display live user data, make sure “no data scenario” is handled for new users | Sprint 5: Dashboard Development | Completed
Backend: CRUD API for rooms (user → rooms) | Sprint 4: Map My House Feature | Completed
Frontend: Map My House page, room creation UI, multiple floors | Sprint 4: Map My House Feature | Completed
Link rooms to user accounts | Sprint 4: Map My House Feature | Completed
Configure “My Appliiances” to work alongside Map my house | Sprint 4: Map My House Feature | Completed
Appliance DB: Create JSON file with list of household appliances which users can assign in “my Appliances” | Sprint 3: My Appliances Feature | Completed
Backend: CRUD API for appliances (room → appliances) | Sprint 3: My Appliances Feature | Completed
Frontend: Appliance assignment, selection from DB | Sprint 3: My Appliances Feature | Completed
Store appliance usage hours and wattage | Sprint 3: My Appliances Feature | Completed
Test user flows from room creation → appliance assignment | Sprint 3: My Appliances Feature | Completed
Backend: API endpoints to calculate room consumption and top 5 appliances | Sprint 6: Watch Your Watts page | Completed
Frontend: Pie charts (Recharts/Chart.js) for rooms | Sprint 6: Watch Your Watts page | Completed
Cost forecasting based on appliance usage | Sprint 6: Watch Your Watts page | Completed
Test correctness of calculations and visuals | Sprint 6: Watch Your Watts page | Completed
Bill Vault Implementation | Sprint 6: Watch Your Watts page | Completed
Test all core API connections and end-to-end user flows | Sprint 8: Integration & Security Hardening | Completed
Add frontend and backend input validation for all key forms | Sprint 8: Integration & Security Hardening | Completed
Review password hashing, JWT expiry and access to protected endpoints | Sprint 8: Integration & Security Hardening | Completed
Improve error handling and user-facing error messages | Sprint 8: Integration & Security Hardening | Completed
Check CORS, environment variable usage, and sensitive data handling | Sprint 8: Integration & Security Hardening | Completed
Document security measures in SECURITY_NOTES.md | Sprint 8: Integration & Security Hardening | Completed
Write unit tests for core backend services using JUnit and Mockito | Sprint 9: Testing & Debugging | Not Started
Write integration tests for authentication, room management, appliance management and usage/insights APIs | Sprint 9: Testing & Debugging | Not Started
Test forecasting and cost-calculation outputs against sample input data and expected results | Sprint 9: Testing & Debugging | Not Started
Test database CRUD behaviour, relational consistency, and edge-case scenarios | Sprint 9: Testing & Debugging | Not Started
Debug defects identified during testing and retest affected functionality | Sprint 9: Testing & Debugging | Not Started
Perform system testing of full user journeys from signup/login through dashboard and forecasting features | Sprint 9: Testing & Debugging | Not Started
Prepare a test report summarising test cases, results, bugs found, fixes applied, and remaining limitations | Sprint 9: Testing & Debugging | Not Started
Regression tests of all modules | Sprint 12: Final Testing & Submission Polish | Not Started
Proofread documentation, check academic compliance | Sprint 12: Final Testing & Submission Polish | Not Started
Final code review and GitHub commit history clean-up | Sprint 12: Final Testing & Submission Polish | Not Started
Prepare submission zip and presentation slides | Sprint 12: Final Testing & Submission Polish | Not Started
Add optional features, Optimise performance (frontend rendering, backend queries) Update diagrams and architecture documents | Sprint 10: Final Feature Enhancements | Not Started
Changeover from SQLite to PostgreSQL | Sprint 10: Final Feature Enhancements | Completed
Presentation Slides | Mid Point Requirements | Completed
Update Project Proposal | Mid Point Requirements | Completed
Technical Report | Mid Point Requirements | Completed
Technical Report | Sprint 11: Documentation & Deployment Prep | Not Started
Research Deployment methods | Sprint 11: Documentation & Deployment Prep | Not Started
Task |  | Not Started
Built Smart Insights backend API | Sprint 7: Smart Insights | Completed
implement rules based UI insights engine | Sprint 7: Smart Insights | Completed
Implemented ranking, dedupes and filters | Sprint 7: Smart Insights | Completed
Nice UX flow implementated | Sprint 7: Smart Insights | Completed
added navbar, seperate from watch your watts | Sprint 7: Smart Insights | Completed